## Record
Time Recording Log
|  | Total Time: | 9.9167
Date | Start Time | Stop Time | Delta | Activity | Task | Estimated Time | Remaing
2020-02-04 |  |  | 1 | logo
2020-02-05 |  |  | 0.25 | added logo
2020-02-06 |  |  | 0.25 | updated logo sizes
2020-02-10 |  |  | 2 | about me page
2020-02-11 | 19:00 | 20:00 | 1 | Built connect 4 board | 1a | 1 | 0
2020-02-12 |  |  | 0.25 | Fixed experience text
2020-02-25 | 6:00 | 6:35 | 0.58333 | Built connect 4 board | 1a | 1 | -0.58
2020-02-25 | 10:45 | 11:36 | 0.85 | Setting up products
2020-02-26 | 11:36 | 13:21 | 1.75 | Added a products page
2020-03-03 | 11:00 | 12:00 | 1 | Made buttons work | 1b | 1 | 0
2020-03-03 | 21:48 | 22:47 | 0.98333 | The buttons are finished | 1b | 1 | 1

## Tasks
| Tasks |  |  | 22.83
1 | Connect 4 Game |  | 6
a | Build Board | 1
b | Make the buttons work | 1
c | Format the game in CSS | 0.5
d | Code the game logic | 3.5
2 | Connect 4 Computer |  | 9.83
a | Feed computer board array | 0.33
b | Write Mini Max Functinos | 4
c | Write Score Function | 2.5
d | Buttons for limit depth | 2
e | get depth input | 1
3 | Connect 4 Finish
a | Test | 0.5
b | Test | 0.5
c | Test | 0.5
4 | Nim Game |  | 7
a | Build the board | 2.5
b | Make the buttons work | 1
c | research nim sum | 1.5
d | code the nim sum comp | 2